## Sheet1
Date | Hours | Category | Comment
2013-05-11 | 1 | Preparation | Skype meeting to organize team roles and split work.
2013-05-13 | 0.25 | Design | Review UCD for delivery 0.
2013-05-15 | 0.25 | Design | Review system overview for delivery 0.
2013-05-17 | 0.25 | Documentation | Final review for delivery 0 document.
2013-05-17 | 0.5 | Preparation | Setup computer for project development.
Downloaded Visual Studio 2012 and cloned git repository at https://github.com/Darkneon/C-Ker
2013-05-29 | 0.5 | Preparation | Meeting to split the work for delivery 1.
2013-06-01 | 0.25 | Documentation | Review software requirements document outline.
2013-06-01 | 4 | Code and test | Setup C# WPF project and implement initial GUI design.
2013-06-02 | 0.25 | Documentation | Review software requirements document draft.
2013-06-03 | 1 | Documentation | Write a third of the use cases for the system.
2013-06-04 | 0.5 | Documentation | Review use cases and use case diagram.
2013-06-05 | 0.25 | Documentation | Final review for delivery 1 document.
2013-07-03 | 0.25 | Preparation | Meeting to split the work for delivery 2.
2013-07-04 | 0.5 | Preparation | Created various .vsf scenario files for later use.
2013-07-11 | 4 | Code and test | Implement filtering and sorting of vessels feature.
2013-07-18 | 1 | Design | Skype meeting to discuss detailed design for delivery 2.
2013-07-19 | 0.5 | Documentation | Update all use cases from previous delivery.
2013-07-19 | 1 | Documentation | Create complete class diagram for the system.
2013-07-19 | 2 | Documentation | Write detailed design section of project design document.
2013-07-22 | 1 | Documentation | Update class diagram and detailed design after review.
2013-07-24 | 3 | Documentation | Help complete and polish the document in latex.
2013-07-31 | 0.25 | Preparation | Meeting to discuss remaining work before the demo.
2013-08-02 | 4 | Code and test | Refactor code to use MVP architecture design pattern.
2013-08-03 | 2 | Code and test | Implement vessel alarm colours in table list view.
2013-08-05 | 1 | Code and test | Write unit test cases for presenters and authenticator.
2013-08-06 | 4 | Code and test | Fix bugs and improve user interface elements.
2013-08-07 | 4 | Code and test | Make final polishing changes before demo.
2013-08-08 | 2.5 | Documentation | Write test coverage section in project testing document.
2013-08-10 | 2 | Documentation | Write individual report.
2013-08-12 | 0.25 | Documentation | Final review for delivery 3 document.
42.25